## Sheet1
Schedule Management
Project Name: Health and Wellness App Development | Date: 08/23/2020
Estimated Hours per person
Work Breakdown Structure Categories | Start Date | End Date | Responsible | Annie | Sindhuja | Alekhya | Tarun | Vigneshwar | Neelesh | Total Hours
1. Initiating | 2020-08-23 | 2020-08-24 | Team | 1 | 1 | 1 | 1 | 3 | 2 | 9
2. Planning | 2020-08-24 | 11/31/2020 | Team | 2 | 2 | 2 | 2 | 2 | 2 | 12
3. Designing | 2020-08-25 | 2020-09-15 | Sindhuja | 2 | 2 | 2 | 2 | 2 | 1 | 11
3.1 UI Design | 2020-09-16 | 2020-10-15 | Team |  |  |  |  | 4 |  | 4
3.2 Synthesis of Design | 2020-10-16 | 2020-11-04 | Vigneshwar |  |  | 4 |  |  |  | 4
3.3 Implementation Iteration | 2020-11-05 | 2020-11-26 | Alekhya | 1 | 1 |  | 1 |  |  | 3
3.4 Early release and Contract finalization | 2020-11-27 | 11/31/2020 | Team | 1 | 1 |  |  |  | 1 | 3
4. Implementation | 2020-01-20 | 2020-03-30 | Team | 2 | 2 | 2 | 2 | 2 | 2 | 12
4.1 Application Development | 2020-01-20 | 2020-02-05 | Team |  |  |  | 4 | 2 |  | 6
4.2 PWA Implementation | 2020-02-06 | 2020-02-28 | Annie |  | 1 | 1 | 1 |  |  | 3
4.3 Android/iOS Implementation | 2020-03-01 | 2020-03-30 | Tarun | [5 empty] | 3 | 3
5. Monitoring and Controlling | 2020-04-03 | 2020-04-17 | Team | 2 | 2 | 2 | 2 | 2 | 1 | 11
6. Closing | 2020-04-18 | 2020-05-01 | Neelesh | 2 | 2 | 1 | 2 | 1 | 2 | 10
Total | [9 empty] | 91