## Sheet1
Cost Estimate
Project Name: Health and Wellness App Development (HWAD) | Date: 08/23/2020
WBS Categories | Total Team Cost | Number of hours per week | Total cost per week | Total cost for three sprints | Designation | $/hour
1. Initiating | 365 | 9 | 3285 | 19710 | Team Leader | 75
2. Planning | 365 | 12 | 4380 | 26280 | Project Manager | 65
3. Designing | 365 | 11 | 4015 | 24090 | Full stack Developer | 60
3.1 UI Design |  | 4 | 0 | 0 | UI Developer | 55
3.2 Synthesis of Design |  | 4 | 0 | 0 | Database Engineer | 55
3.3 Implementation Iteration |  | 3 | 0 | 0 | Front end Developer | 55
3.4 Early release and Contract finalization |  | 3 | 0 | 0
4. Implementation | 365 | 12 | 4380 | 26280
4.1 Application Development |  | 6 | 0 | 0
4.2 PWA Implementation |  | 3 | 0 | 0
4.3 Android/iOS Implementation |  | 3 | 0 | 0
5. Monitoring and Controlling | 365 | 11 | 4015 | 24090
6. Closing | 365 | 10 | 3650 | 21900
Total |  |  |  | 142350